## Process Analysis
PID | Batch | Area | Site A | Site B | Project Status | Project State | Site Tier | Process | Duration | Process Key
SAMPLE-0001 | Batch 1B | Area B | Site A1 | Site B1 | Active | Project Completed | Feeder | IWO Process | 58 | IWO Process-Feeder
SAMPLE-0001 | Batch 1B | Area B | Site A1 | Site B1 | Active | Project Completed | Feeder | Survey Duration | 13 | Survey Duration-Feeder
SAMPLE-0001 | Batch 1B | Area B | Site A1 | Site B1 | Active | Project Completed | Feeder | Design Input | 141 | Design Input-Feeder
SAMPLE-0001 | Batch 1B | Area B | Site A1 | Site B1 | Active | Project Completed | Feeder | AFI Process | 126 | AFI Process-Feeder
SAMPLE-0001 | Batch 1B | Area B | Site A1 | Site B1 | Active | Project Completed | Feeder | RTA Submission | 115 | RTA Submission-Feeder
SAMPLE-0001 | Batch 1B | Area B | Site A1 | Site B1 | Active | Project Completed | Feeder | RTA Securing | 72 | RTA Securing-Feeder
SAMPLE-0001 | Batch 1B | Area B | Site A1 | Site B1 | Active | Project Completed | Feeder | WO Procurement | 53 | WO Procurement-Feeder
SAMPLE-0001 | Batch 1B | Area B | Site A1 | Site B1 | Active | Project Completed | Feeder | Implementation | 280 | Implementation-Feeder
SAMPLE-0001 | Batch 1B | Area B | Site A1 | Site B1 | Active | Project Completed | Feeder | TA Prep | 45 | TA Prep-Feeder
SAMPLE-0001 | Batch 1B | Area B | Site A1 | Site B1 | Active | Project Completed | Feeder | TA Process | 217 | TA Process-Feeder
SAMPLE-0002 | Batch 2A | Area C | Site A2 | Site B2 | Active | On Going | Main FOC | IWO Process | 17 | IWO Process-Main FOC
SAMPLE-0002 | Batch 2A | Area C | Site A2 | Site B2 | Active | On Going | Main FOC | Survey Duration | 16 | Survey Duration-Main FOC
SAMPLE-0002 | Batch 2A | Area C | Site A2 | Site B2 | Active | On Going | Main FOC | Design Input | 48 | Design Input-Main FOC
SAMPLE-0002 | Batch 2A | Area C | Site A2 | Site B2 | Active | On Going | Main FOC | AFI Process | 112 | AFI Process-Main FOC
SAMPLE-0002 | Batch 2A | Area C | Site A2 | Site B2 | Active | On Going | Main FOC | RTA Submission | 120 | RTA Submission-Main FOC
SAMPLE-0002 | Batch 2A | Area C | Site A2 | Site B2 | Active | On Going | Main FOC | RTA Securing | 259 | RTA Securing-Main FOC
SAMPLE-0002 | Batch 2A | Area C | Site A2 | Site B2 | Active | On Going | Main FOC | WO Procurement | 14 | WO Procurement-Main FOC
SAMPLE-0002 | Batch 2A | Area C | Site A2 | Site B2 | Active | On Going | Main FOC | Implementation | 288 | Implementation-Main FOC
SAMPLE-0002 | Batch 2A | Area C | Site A2 | Site B2 | Active | On Going | Main FOC | TA Prep | 102 | TA Prep-Main FOC
SAMPLE-0002 | Batch 2A | Area C | Site A2 | Site B2 | Active | On Going | Main FOC | TA Process | 280 | TA Process-Main FOC
SAMPLE-0003 | Batch 2B | Area D | Site A3 | Site B3 | Inactive | On Hold | Tailing | IWO Process | 215 | IWO Process-Tailing
SAMPLE-0003 | Batch 2B | Area D | Site A3 | Site B3 | Inactive | On Hold | Tailing | Survey Duration | 113 | Survey Duration-Tailing
SAMPLE-0003 | Batch 2B | Area D | Site A3 | Site B3 | Inactive | On Hold | Tailing | Design Input | 230 | Design Input-Tailing
SAMPLE-0003 | Batch 2B | Area D | Site A3 | Site B3 | Inactive | On Hold | Tailing | AFI Process | 143 | AFI Process-Tailing
SAMPLE-0003 | Batch 2B | Area D | Site A3 | Site B3 | Inactive | On Hold | Tailing | RTA Submission | 4 | RTA Submission-Tailing
SAMPLE-0003 | Batch 2B | Area D | Site A3 | Site B3 | Inactive | On Hold | Tailing | RTA Securing | 82 | RTA Securing-Tailing
SAMPLE-0003 | Batch 2B | Area D | Site A3 | Site B3 | Inactive | On Hold | Tailing | WO Procurement | 217 | WO Procurement-Tailing
SAMPLE-0003 | Batch 2B | Area D | Site A3 | Site B3 | Inactive | On Hold | Tailing | Implementation | 175 | Implementation-Tailing
SAMPLE-0003 | Batch 2B | Area D | Site A3 | Site B3 | Inactive | On Hold | Tailing | TA Prep | 143 | TA Prep-Tailing
SAMPLE-0003 | Batch 2B | Area D | Site A3 | Site B3 | Inactive | On Hold | Tailing | TA Process | 80 | TA Process-Tailing
SAMPLE-0004 | Batch 3A | Area E | Site A4 | Site B4 | Active | Project Completed | Feeder | IWO Process | 111 | IWO Process-Feeder
SAMPLE-0004 | Batch 3A | Area E | Site A4 | Site B4 | Active | Project Completed | Feeder | Survey Duration | 173 | Survey Duration-Feeder
SAMPLE-0004 | Batch 3A | Area E | Site A4 | Site B4 | Active | Project Completed | Feeder | Design Input | 53 | Design Input-Feeder
SAMPLE-0004 | Batch 3A | Area E | Site A4 | Site B4 | Active | Project Completed | Feeder | AFI Process | 48 | AFI Process-Feeder
SAMPLE-0004 | Batch 3A | Area E | Site A4 | Site B4 | Active | Project Completed | Feeder | RTA Submission | 195 | RTA Submission-Feeder
SAMPLE-0004 | Batch 3A | Area E | Site A4 | Site B4 | Active | Project Completed | Feeder | RTA Securing | 50 | RTA Securing-Feeder
SAMPLE-0004 | Batch 3A | Area E | Site A4 | Site B4 | Active | Project Completed | Feeder | WO Procurement | 184 | WO Procurement-Feeder
SAMPLE-0004 | Batch 3A | Area E | Site A4 | Site B4 | Active | Project Completed | Feeder | Implementation | 177 | Implementation-Feeder
SAMPLE-0004 | Batch 3A | Area E | Site A4 | Site B4 | Active | Project Completed | Feeder | TA Prep | 136 | TA Prep-Feeder
SAMPLE-0004 | Batch 3A | Area E | Site A4 | Site B4 | Active | Project Completed | Feeder | TA Process | 23 | TA Process-Feeder
SAMPLE-0005 | Batch 1A | Area A | Site A5 | Site B5 | Active | Project Completed | Main FOC | IWO Process | 236 | IWO Process-Main FOC
SAMPLE-0005 | Batch 1A | Area A | Site A5 | Site B5 | Active | Project Completed | Main FOC | Survey Duration | 275 | Survey Duration-Main FOC
SAMPLE-0005 | Batch 1A | Area A | Site A5 | Site B5 | Active | Project Completed | Main FOC | Design Input | 64 | Design Input-Main FOC
SAMPLE-0005 | Batch 1A | Area A | Site A5 | Site B5 | Active | Project Completed | Main FOC | AFI Process | 194 | AFI Process-Main FOC
SAMPLE-0005 | Batch 1A | Area A | Site A5 | Site B5 | Active | Project Completed | Main FOC | RTA Submission | 41 | RTA Submission-Main FOC
SAMPLE-0005 | Batch 1A | Area A | Site A5 | Site B5 | Active | Project Completed | Main FOC | RTA Securing | 283 | RTA Securing-Main FOC
SAMPLE-0005 | Batch 1A | Area A | Site A5 | Site B5 | Active | Project Completed | Main FOC | WO Procurement | 151 | WO Procurement-Main FOC
SAMPLE-0005 | Batch 1A | Area A | Site A5 | Site B5 | Active | Project Completed | Main FOC | Implementation | 186 | Implementation-Main FOC
SAMPLE-0005 | Batch 1A | Area A | Site A5 | Site B5 | Active | Project Completed | Main FOC | TA Prep | 296 | TA Prep-Main FOC
SAMPLE-0005 | Batch 1A | Area A | Site A5 | Site B5 | Active | Project Completed | Main FOC | TA Process | 99 | TA Process-Main FOC
SAMPLE-0006 | Batch 1B | Area B | Site A6 | Site B6 | Active | On Going | Tailing | IWO Process | 36 | IWO Process-Tailing
SAMPLE-0006 | Batch 1B | Area B | Site A6 | Site B6 | Active | On Going | Tailing | Survey Duration | 24 | Survey Duration-Tailing
SAMPLE-0006 | Batch 1B | Area B | Site A6 | Site B6 | Active | On Going | Tailing | Design Input | 117 | Design Input-Tailing
SAMPLE-0006 | Batch 1B | Area B | Site A6 | Site B6 | Active | On Going | Tailing | AFI Process | 149 | AFI Process-Tailing
SAMPLE-0006 | Batch 1B | Area B | Site A6 | Site B6 | Active | On Going | Tailing | RTA Submission | 41 | RTA Submission-Tailing
SAMPLE-0006 | Batch 1B | Area B | Site A6 | Site B6 | Active | On Going | Tailing | RTA Securing | 120 | RTA Securing-Tailing
SAMPLE-0006 | Batch 1B | Area B | Site A6 | Site B6 | Active | On Going | Tailing | WO Procurement | 52 | WO Procurement-Tailing
SAMPLE-0006 | Batch 1B | Area B | Site A6 | Site B6 | Active | On Going | Tailing | Implementation | 195 | Implementation-Tailing
SAMPLE-0006 | Batch 1B | Area B | Site A6 | Site B6 | Active | On Going | Tailing | TA Prep | 143 | TA Prep-Tailing
SAMPLE-0006 | Batch 1B | Area B | Site A6 | Site B6 | Active | On Going | Tailing | TA Process | 233 | TA Process-Tailing
SAMPLE-0007 | Batch 2A | Area C | Site A7 | Site B7 | Inactive | On Hold | Feeder | IWO Process | 187 | IWO Process-Feeder
SAMPLE-0007 | Batch 2A | Area C | Site A7 | Site B7 | Inactive | On Hold | Feeder | Survey Duration | 84 | Survey Duration-Feeder
SAMPLE-0007 | Batch 2A | Area C | Site A7 | Site B7 | Inactive | On Hold | Feeder | Design Input | 190 | Design Input-Feeder
SAMPLE-0007 | Batch 2A | Area C | Site A7 | Site B7 | Inactive | On Hold | Feeder | AFI Process | 182 | AFI Process-Feeder
SAMPLE-0007 | Batch 2A | Area C | Site A7 | Site B7 | Inactive | On Hold | Feeder | RTA Submission | 108 | RTA Submission-Feeder
SAMPLE-0007 | Batch 2A | Area C | Site A7 | Site B7 | Inactive | On Hold | Feeder | RTA Securing | 137 | RTA Securing-Feeder
SAMPLE-0007 | Batch 2A | Area C | Site A7 | Site B7 | Inactive | On Hold | Feeder | WO Procurement | 37 | WO Procurement-Feeder
SAMPLE-0007 | Batch 2A | Area C | Site A7 | Site B7 | Inactive | On Hold | Feeder | Implementation | 88 | Implementation-Feeder
SAMPLE-0007 | Batch 2A | Area C | Site A7 | Site B7 | Inactive | On Hold | Feeder | TA Prep | 274 | TA Prep-Feeder
SAMPLE-0007 | Batch 2A | Area C | Site A7 | Site B7 | Inactive | On Hold | Feeder | TA Process | 126 | TA Process-Feeder
SAMPLE-0008 | Batch 2B | Area D | Site A8 | Site B8 | Active | Project Completed | Main FOC | IWO Process | 84 | IWO Process-Main FOC
SAMPLE-0008 | Batch 2B | Area D | Site A8 | Site B8 | Active | Project Completed | Main FOC | Survey Duration | 237 | Survey Duration-Main FOC
SAMPLE-0008 | Batch 2B | Area D | Site A8 | Site B8 | Active | Project Completed | Main FOC | Design Input | 195 | Design Input-Main FOC
SAMPLE-0008 | Batch 2B | Area D | Site A8 | Site B8 | Active | Project Completed | Main FOC | AFI Process | 139 | AFI Process-Main FOC
SAMPLE-0008 | Batch 2B | Area D | Site A8 | Site B8 | Active | Project Completed | Main FOC | RTA Submission | 286 | RTA Submission-Main FOC
SAMPLE-0008 | Batch 2B | Area D | Site A8 | Site B8 | Active | Project Completed | Main FOC | RTA Securing | 113 | RTA Securing-Main FOC
SAMPLE-0008 | Batch 2B | Area D | Site A8 | Site B8 | Active | Project Completed | Main FOC | WO Procurement | 167 | WO Procurement-Main FOC
SAMPLE-0008 | Batch 2B | Area D | Site A8 | Site B8 | Active | Project Completed | Main FOC | Implementation | 29 | Implementation-Main FOC
SAMPLE-0008 | Batch 2B | Area D | Site A8 | Site B8 | Active | Project Completed | Main FOC | TA Prep | 118 | TA Prep-Main FOC
SAMPLE-0008 | Batch 2B | Area D | Site A8 | Site B8 | Active | Project Completed | Main FOC | TA Process | 17 | TA Process-Main FOC
SAMPLE-0009 | Batch 3A | Area E | Site A9 | Site B9 | Active | Project Completed | Tailing | IWO Process | 162 | IWO Process-Tailing
SAMPLE-0009 | Batch 3A | Area E | Site A9 | Site B9 | Active | Project Completed | Tailing | Survey Duration | 206 | Survey Duration-Tailing
SAMPLE-0009 | Batch 3A | Area E | Site A9 | Site B9 | Active | Project Completed | Tailing | Design Input | 138 | Design Input-Tailing
SAMPLE-0009 | Batch 3A | Area E | Site A9 | Site B9 | Active | Project Completed | Tailing | AFI Process | 34 | AFI Process-Tailing
SAMPLE-0009 | Batch 3A | Area E | Site A9 | Site B9 | Active | Project Completed | Tailing | RTA Submission | 109 | RTA Submission-Tailing
SAMPLE-0009 | Batch 3A | Area E | Site A9 | Site B9 | Active | Project Completed | Tailing | RTA Securing | 291 | RTA Securing-Tailing
SAMPLE-0009 | Batch 3A | Area E | Site A9 | Site B9 | Active | Project Completed | Tailing | WO Procurement | 162 | WO Procurement-Tailing
SAMPLE-0009 | Batch 3A | Area E | Site A9 | Site B9 | Active | Project Completed | Tailing | Implementation | 109 | Implementation-Tailing
SAMPLE-0009 | Batch 3A | Area E | Site A9 | Site B9 | Active | Project Completed | Tailing | TA Prep | 256 | TA Prep-Tailing
SAMPLE-0009 | Batch 3A | Area E | Site A9 | Site B9 | Active | Project Completed | Tailing | TA Process | 203 | TA Process-Tailing
SAMPLE-0010 | Batch 1A | Area A | Site A10 | Site B10 | Active | On Going | Feeder | IWO Process | 235 | IWO Process-Feeder
SAMPLE-0010 | Batch 1A | Area A | Site A10 | Site B10 | Active | On Going | Feeder | Survey Duration | 74 | Survey Duration-Feeder
SAMPLE-0010 | Batch 1A | Area A | Site A10 | Site B10 | Active | On Going | Feeder | Design Input | 136 | Design Input-Feeder
SAMPLE-0010 | Batch 1A | Area A | Site A10 | Site B10 | Active | On Going | Feeder | AFI Process | 72 | AFI Process-Feeder
SAMPLE-0010 | Batch 1A | Area A | Site A10 | Site B10 | Active | On Going | Feeder | RTA Submission | 127 | RTA Submission-Feeder
SAMPLE-0010 | Batch 1A | Area A | Site A10 | Site B10 | Active | On Going | Feeder | RTA Securing | 288 | RTA Securing-Feeder
SAMPLE-0010 | Batch 1A | Area A | Site A10 | Site B10 | Active | On Going | Feeder | WO Procurement | 276 | WO Procurement-Feeder
SAMPLE-0010 | Batch 1A | Area A | Site A10 | Site B10 | Active | On Going | Feeder | Implementation | 135 | Implementation-Feeder
SAMPLE-0010 | Batch 1A | Area A | Site A10 | Site B10 | Active | On Going | Feeder | TA Prep | 300 | TA Prep-Feeder
SAMPLE-0010 | Batch 1A | Area A | Site A10 | Site B10 | Active | On Going | Feeder | TA Process | 220 | TA Process-Feeder

## Site Masterlist
PID | Project Status | Project Type | Batch | Region | Area | City | Barangay | BTS Type | Site A | Site B | Cluster | Ring | Subcon | IWO Request | IWO Approval | Survey Done Date | AFI Submitted | AFI Approval | RTA Submitted | RTA Approval | WO/BOQ Submitted | Acceptance | TA Submitted | TA Approval | Project Progress | IWO Process | Survey Duration | Design Input | AFI Process | RTA Submission | RTA Securing | WO Procurement | Implementation | TA Prep | TA Process | Site Tier | Project State | TA Approval Helper (YYYY-MM) | TA Approval Helper (YYYY)
SAMPLE-0001 | Active | FTTBTS | Batch 1B | Region X | Area B | City Beta | Barangay 1 | BTS | Site A1 | Site B1 | Cluster 2 | Ring 2 | SubconX | 2019-01-25 | 2019-02-01 | 2019-03-03 | 2019-03-04 | 2019-03-18 | 2019-03-19 | 2019-04-18 | 2019-04-20 | 2019-07-29 | 2019-08-05 | 2019-08-19 | Project Completed | 7 | 30 | 5 | 14 | 7 | 30 | 7 | 179 | 7 | 14 | Feeder | Project Completed | 2019-09 | 2019
SAMPLE-0002 | Active | FTTBTS | Batch 2A | Region X | Area C | City Gamma | Barangay 2 | BTS | Site A2 | Site B2 | Cluster 3 | Ring 3 | SubconY | 2019-02-04 | 2019-02-11 | 2019-03-13 | 2019-03-14 | 2019-03-28 | 2019-03-29 | 2019-04-28 | 2019-04-30 | 2019-08-08 | 2019-08-15 | 2019-08-29 | Project Completed | 7 | 30 | 5 | 14 | 7 | 30 | 7 | 132 | 7 | 14 | Main FOC | Project Completed | 2019-09 | 2019
SAMPLE-0003 | Active | FTTBTS | Batch 2B | Region X | Area D | City Delta | Barangay 3 | BTS | Site A3 | Site B3 | Cluster 1 | Ring 1 | SubconZ | 2019-02-14 | 2019-02-21 | 2019-03-23 | 2019-03-24 | 2019-04-07 | 2019-04-08 | 2019-05-08 | 2019-05-10 | 2019-08-18 | 2019-08-25 | 2019-09-08 | Project Completed | 7 | 30 | 5 | 14 | 7 | 30 | 7 | 122 | 7 | 14 | Tailing | Project Completed | 2019-09 | 2019
SAMPLE-0004 | Active | FTTBTS | Batch 3A | Region X | Area E | City Alpha | Barangay 4 | BTS | Site A4 | Site B4 | Cluster 2 | Ring 2 | Inhouse | 2019-02-24 | 2019-03-03 | 2019-04-02 | 2019-04-03 | 2019-04-17 | 2019-04-18 | 2019-05-18 | 2019-05-20 | 2019-08-28 | 2019-09-04 | 2019-09-18 | Project Completed | 7 | 30 | 5 | 14 | 7 | 30 | 7 | 86 | 7 | 14 | Feeder | Project Completed | 2019-09 | 2019
SAMPLE-0005 | Active | FTTBTS | Batch 1A | Region X | Area A | City Beta | Barangay 5 | BTS | Site A5 | Site B5 | Cluster 3 | Ring 3 | SubconX | 2019-03-06 | 2019-03-13 | 2019-04-12 | 2019-04-13 | 2019-04-27 | 2019-04-28 | 2019-05-28 | 2019-05-30 | 2019-09-07 | 2019-09-14 | 2019-09-28 | Project Completed | 7 | 30 | 5 | 14 | 7 | 30 | 7 | 65 | 7 | 14 | Main FOC | Project Completed | 2019-09 | 2019
SAMPLE-0006 | Active | FTTBTS | Batch 1B | Region X | Area B | City Gamma | Barangay 6 | BTS | Site A6 | Site B6 | Cluster 1 | Ring 1 | SubconY | 2019-03-16 | 2019-03-23 | 2019-04-22 | 2019-04-23 | 2019-05-07 | 2019-05-08 | 2019-06-07 | 2019-06-09 | 2019-09-17 | 2019-09-24 | 2019-10-08 | Project Completed | 7 | 30 | 5 | 14 | 7 | 30 | 7 | 160 | 7 | 14 | Tailing | Project Completed | 2019-09 | 2019
SAMPLE-0007 | Active | FTTBTS | Batch 2A | Region X | Area C | City Delta | Barangay 7 | BTS | Site A7 | Site B7 | Cluster 2 | Ring 2 | SubconZ | 2019-03-26 | 2019-04-02 | 2019-05-02 | 2019-05-03 | 2019-05-17 | 2019-05-18 | 2019-06-17 | 2019-06-19 | 2019-09-27 | 2019-10-04 | 2019-10-18 | Project Completed | 7 | 30 | 5 | 14 | 7 | 30 | 7 | 156 | 7 | 14 | Feeder | Project Completed | 2019-09 | 2019
SAMPLE-0008 | Active | FTTBTS | Batch 2B | Region X | Area D | City Alpha | Barangay 8 | BTS | Site A8 | Site B8 | Cluster 3 | Ring 3 | Inhouse | 2019-04-05 | 2019-04-12 | 2019-05-12 | 2019-05-13 | 2019-05-27 | 2019-05-28 | 2019-06-27 | 2019-06-29 | 2019-10-07 | 2019-10-14 | 2019-10-28 | Project Completed | 7 | 30 | 5 | 14 | 7 | 30 | 7 | 53 | 7 | 14 | Main FOC | Project Completed | 2019-09 | 2019
SAMPLE-0009 | Active | FTTBTS | Batch 3A | Region X | Area E | City Beta | Barangay 9 | BTS | Site A9 | Site B9 | Cluster 1 | Ring 1 | SubconX | 2019-04-15 | 2019-04-22 | 2019-05-22 | 2019-05-23 | 2019-06-06 | 2019-06-07 | 2019-07-07 | 2019-07-09 | 2019-10-17 | 2019-10-24 | 2019-11-07 | Project Completed | 7 | 30 | 5 | 14 | 7 | 30 | 7 | 42 | 7 | 14 | Tailing | Project Completed | 2019-09 | 2019
SAMPLE-0010 | Active | FTTBTS | Batch 1A | Region X | Area A | City Gamma | Barangay 10 | BTS | Site A10 | Site B10 | Cluster 2 | Ring 2 | SubconY | 2019-04-25 | 2019-05-02 | 2019-06-01 | 2019-06-02 | 2019-06-16 | 2019-06-17 | 2019-07-17 | 2019-07-19 | 2019-10-27 | 2019-11-03 | 2019-11-17 | Project Completed | 7 | 30 | 5 | 14 | 7 | 30 | 7 | 58 | 7 | 14 | Feeder | Project Completed | 2019-09 | 2019

## Benchmark
Site Tier | Process | Process Order | Duration Benchmark | Process Key
Main FOC | IWO Process | 1 | 7 | IWO Process-Main FOC
Main FOC | Survey Duration | 2 | 90 | Survey Duration-Main FOC
Main FOC | Design Input | 3 | 14 | Design Input-Main FOC
Main FOC | AFI Process | 4 | 14 | AFI Process-Main FOC
Main FOC | RTA Submission | 5 | 14 | RTA Submission-Main FOC
Main FOC | RTA Securing | 6 | 90 | RTA Securing-Main FOC
Main FOC | WO Procurement | 7 | 7 | WO Procurement-Main FOC
Main FOC | Implementation | 8 | 300 | Implementation-Main FOC
Main FOC | TA Prep | 9 | 14 | TA Prep-Main FOC
Main FOC | TA Process | 10 | 14 | TA Process-Main FOC
Tailing | IWO Process | 1 | 7 | IWO Process-Tailing
Tailing | Survey Duration | 2 | 30 | Survey Duration-Tailing
Tailing | Design Input | 3 | 2 | Design Input-Tailing
Tailing | AFI Process | 4 | 14 | AFI Process-Tailing
Tailing | RTA Submission | 5 | 7 | RTA Submission-Tailing
Tailing | RTA Securing | 6 | 30 | RTA Securing-Tailing
Tailing | WO Procurement | 7 | 7 | WO Procurement-Tailing
Tailing | Implementation | 8 | 60 | Implementation-Tailing
Tailing | TA Prep | 9 | 14 | TA Prep-Tailing
Tailing | TA Process | 10 | 14 | TA Process-Tailing
Feeder | IWO Process | 1 | 7 | IWO Process-Feeder
Feeder | Survey Duration | 2 | 30 | Survey Duration-Feeder
Feeder | Design Input | 3 | 7 | Design Input-Feeder
Feeder | AFI Process | 4 | 14 | AFI Process-Feeder
Feeder | RTA Submission | 5 | 7 | RTA Submission-Feeder
Feeder | RTA Securing | 6 | 60 | RTA Securing-Feeder
Feeder | WO Procurement | 7 | 7 | WO Procurement-Feeder
Feeder | Implementation | 8 | 150 | Implementation-Feeder
Feeder | TA Prep | 9 | 14 | TA Prep-Feeder
Feeder | TA Process | 10 | 14 | TA Process-Feeder

## Subcon Helper
AREA | Subcon Name
Area A | Inhouse
Area A | SubconX
Area B | Inhouse
Area B | SubconY
Area C | Inhouse
Area C | SubconZ
Area D | Inhouse
Area D | SubconX
Area E | Inhouse
Area E | SubconY

## Manpower
AREA | SUBCON NAME | REGION | PROJECT | Design Man power | Admin | Implementation Supervisor | ROW/RTA Officer | Project Count
Area A | Inhouse, SubconX | Region X | FBTS | 4 | 2 | 3 | 2 | 185
Area B | Inhouse, SubconY | Region X | FBTS | 8 | 4 | 5 | 4 | 918
Area C | Inhouse, SubconZ | Region X | FBTS | 2 | 1 | 2 | 1 | 34
Area D | Inhouse, SubconX | Region X | FBTS | 6 | 3 | 4 | 4 | 865
Area E | Inhouse, SubconY | Region X | FBTS | 4 | 4 | 3 | 1 | 236